## Foglio1
Date | What we did during the meeting | Work hours | TOT.
2024-03-18 | Introduction to the project, tools to use and deadline set for 03/21 to deliver the presentations with the work plan | 19.00-20.00 | 21.30 h
2024-03-19 | Meeting to clarify ideas on the steps to follow for the project | 16.30-17.30
2024-03-20 | Conclusion of kick-of presentation | 16.00-21.00
2024-03-21 | Meeting to review the presentation | 19.30-20.30
2024-03-23 | Fix the whole presentation | 10.00-13.00 / 14.00-15.30
2024-04-04 | Meeting to review the presentation | 18.30-19.30
2024-04-05 | Fix the whole presentation | 11.30-13.00
2024-04-09 | Setup Airsim | 9.30-12.00
2024-04-15 | Meeting to verify what we did up to now | 18.15-18.45
2024-04-16 | Start to perform object detection and to chose a model | 9.30-12.00